Project Execution Plan

Millbrook Solar & Storage

Liam McAllister  ·  22 April 2026  ·  MB-PM-PLN-0001

# 1. Purpose and scope

This Project Execution Plan (PEP) sets out how Weyland Energy will take Millbrook Solar & Storage from planning through to financial close and the start of construction. It covers the 85 MWp ground-mounted solar farm on single-axis trackers, the co-located 20 MW / 40 MWh battery energy storage system (BESS) and the 3.8 km 132 kV cable route to the Millbrook 132 kV substation operated by NordGrid Transmission. The site covers 142 ha of former arable farmland north of Millbrook village.

The PEP is a living document. It is owned by the Project Manager and reviewed at every Project Board. Changes to scope, budget or key dates above the tolerances in section 6 need Project Board approval and, where they affect the investment case, Investment Committee approval.

# 2. Project summary

| Item | Value |
| --- | --- |
| Installed capacity | 85 MWp DC / 68.4 MWac |
| Export limit (connection offer) | 70 MW at Millbrook 132 kV substation |
| Battery storage | 20 MW / 40 MWh battery energy storage system (BESS) |
| Modules | ~ 158,000 bifacial modules on single-axis trackers |
| Expected generation | 91.3 GWh per year (P50), ~ 26,000 homes |
| Site area | 142 ha (leased, 40 years, lease signed 18 Nov 2025) |
| Planning reference | MDC/2026/0412 – submitted 18 June 2026, decision expected Q1 2027 |
| EPC | SunForge EPC Ltd (preferred bidder) |
| Capex budget | EUR 78 m (incl. EUR 4.4 m contingency) |
| Community fund | EUR 120,000 per year for the operating life |

# 3. Organisation

The project is led by Liam McAllister (Project Manager) and sponsored by Dr. Amara Okafor (CEO). Engineering support comes from Sofie Lindqvist's team, with Mei Tanaka as lead electrical engineer for the grid and BESS design. Community engagement is led by Tom Berger with Grace Mitchell as Community Liaison Officer on the ground. Land and contracts sit with Priya Nair and Lukas Meyer; Charlotte Dubois (Permitting Manager) and Ahmed Rahimi (Grid Connection Specialist) support from the Grid & Permits team.

| Role | Name | Responsibility |
| --- | --- | --- |
| Project Sponsor | Dr. Amara Okafor | Investment case, Board reporting |
| Project Manager | Liam McAllister | Delivery, budget, schedule, planning strategy |
| Engineering Lead | Sofie Lindqvist | Design basis, layout, technical due diligence |
| Lead Electrical Engineer | Mei Tanaka | Grid connection, BESS, single line diagram |
| Community Engagement Lead | Tom Berger | Consultations, community fund, SCI |
| Permitting Manager | Charlotte Dubois | Planning application, conditions, consultees |
| Legal | Priya Nair | Lease, EPC contract, grid agreements |
| Ecology (external) | Dr. Rachel Moss, Marlow Ecology | EcIA, skylark survey, BNG metric |

# 4. Key milestones

| Milestone | Date | Status |
| --- | --- | --- |
| Land lease signed (Ashcombe Farm and Hollins Farm) | 18 Nov 2025 | Complete |
| Public consultation #1 | 11 Mar 2026 | Complete |
| Public consultation #2 | 20 May 2026 | Complete |
| Planning application MDC/2026/0412 submitted | 18 Jun 2026 | Complete |
| Application validated by Millbrook District Council | 2 Jul 2026 | Complete |
| Public consultation #3 (proposed amendments) | 16 Sep 2026 | Complete |
| Amendment pack submitted to the council | Oct 2026 | In progress |
| Planning committee | Feb 2027 | Planned |
| Planning decision | Q1 2027 | Planned |
| EPC contract award to SunForge EPC Ltd | Q2 2027 | Planned |
| Financial close and notice to proceed | Q3 2027 | Planned |
| Grid connection date (NordGrid offer) | 31 Oct 2028 | Planned |
| Commercial operation | Q4 2028 | Planned |

# 5. Planning strategy

The application is a full planning application under the Town and Country Planning Act. Our strategy rests on three pillars: early and genuine consultation (three public events instead of the usual one or two), a design that visibly responds to feedback, and a biodiversity net gain of 20 % – double the statutory minimum of 10 %.

Glare: independent glint and glare assessment; 3 m hedgerow screening at receptors R04–R06 on Mill Lane.

Construction traffic: temporary haul road from the B4127 so that HGVs do not use the village section of Mill Lane.

Skylark: 46 skylark plots on 12.8 ha of retained arable land, monitored for five years.

Footpath FP14: buffer widened from 15 m to 30 m; field 7 removed from the layout to keep the view to St Mary's Church open.

# 6. Tolerances and change control

| Dimension | Project Manager | Project Board | Investment Committee |
| --- | --- | --- | --- |
| Capex | ± EUR 0.5 m | ± EUR 2.0 m | > EUR 2.0 m |
| Schedule (key milestone) | ± 2 weeks | ± 3 months | > 3 months |
| Installed capacity | ± 0.5 MWp | ± 3 MWp | > 3 MWp |
| Community fund | – | – | Any change |

# 7. Reporting

The Project Manager issues a monthly status report by the third working day of each month and chairs a Project Board on the last Tuesday of each month. Risks are tracked in the Millbrook risk register (MB-RISK-xxx) and escalated to the company risk register when their score exceeds 15.