Event plan

North Sea Energy Summit 2026 · Hamburg · 22–24 September 2026 · Booth B4.210

Noah Fischer  ·  02 February 2026  ·  WE-MC-EVT-2026-01

Owner: Noah Fischer · Core team: Leah Goldberg, Ravi Shah, Henrik Larsen (Business Development), Nina Petrova (Recruiting) · Executive sponsor: Dr. Amara Okafor

# 1. The event

The North Sea Energy Summit 2026 takes place at Hamburg Messe from 22 to 24 September 2026. The organisers expect around 14,000 visitors and 480 exhibitors from the offshore wind, grid, hydrogen and maritime sectors. As a Hamburg company in the middle of building Harrow Bay, this is our home game – and the first time we exhibit with our own stand rather than on a partner booth.

| Item | Detail |
| --- | --- |
| Dates | Tue 22 – Thu 24 September 2026, 09:00–18:00 (Thu until 16:00) |
| Venue | Hamburg Messe, Hall B4 |
| Our booth | B4.210 – island stand, 10 × 8 m (80 m²), aisle 21 |
| Build-up | Sat 19 – Mon 21 September |
| Dismantling | Thu 24 September from 16:30, Fri 25 September |
| Keynote | Dr. Amara Okafor, Main Stage, Tue 22 Sep, 10:30–11:00 |
| Panel | Elena Márquez, 'Delivering offshore wind on time', Stage 2, Wed 23 Sep, 14:00 |
| Reception | Co-hosted networking evening, Wed 23 Sep, 19:00, harbour-side venue |

# 2. Objectives

Keynote – 'From steel to sea: building the North Sea's next decade' (Dr. Amara Okafor)

Panel – Elena Márquez with Halden Turbine Systems, Severn Subsea Cables and NordGrid Transmission

Daily booth talks at 11:30 and 15:30: Harrow Bay construction (Felix Brandt), green hydrogen at Eastholm (Isabel Ferreira), battery storage (Kwame Mensah)

Careers hour Wed 16:00–17:00 with Nina Petrova and Julia Hoffmann

# 5. Budget