## Pipeline
ID | Opportunity | Country | Technology | Capacity (MW) | Stage | Probability | Weighted MW | Lead | Next gate | Gate date | Target COD | Comment
PL-001 | Northfield Offshore Wind | UK | Offshore wind | 1200 | Bid | 0.3 |  | Elena Márquez | Bid submission | 2026-11-27 | 2033 | Leasing round – bid strategy approved by IC 2026-09-23
PL-002 | Harrow Bay Extension | UK | Offshore wind | 300 | Screening | 0.1 |  | Elena Márquez | Seabed agreement application | 2027-03-31 | 2032 | Adjacent to Harrow Bay; shares export corridor
PL-003 | Fehmarn Nord Offshore Wind | DE | Offshore wind | 600 | Bid | 0.3 |  | Henrik Larsen | Tender qualification | 2027-02-15 | 2032 | Federal offshore tender; partner search ongoing
PL-004 | Millbrook Solar & Storage | UK | Solar + BESS | 85 | Permitting | 0.6 |  | Liam McAllister | Planning decision | 2027-03-31 | 2028 | MDC/2026/0412 submitted 2026-06-18
PL-005 | Glenmore Onshore Wind | UK | Onshore wind | 48 | Acquisition | 0.5 |  | Henrik Larsen | Binding offer | 2026-10-30 | 2030 | TDD: P50 147 GWh/a vs. vendor 158 – price adjustment
PL-006 | Ardlochan Wind | UK | Onshore wind | 64 | Development | 0.45 |  | Henrik Larsen | Planning submission | 2027-05-31 | 2030 | LiDAR campaign running since 2026-02
PL-007 | Kestrel Ridge Extension | UK | Onshore wind | 25.2 | Early development | 0.25 |  | David Chen | Scoping opinion | 2027-01-29 | 2030 | 6 × 4.2 MW; uses existing substation
PL-008 | Saltmarsh Solar | UK | Solar PV | 49.9 | Early development | 0.25 |  | Liam McAllister | Land agreement | 2026-12-18 | 2029 | Go decision 2026-06-24
PL-009 | Oakhurst BESS | UK | BESS | 50 | Screening | 0.1 |  | Kwame Mensah | Site visit | 2026-11-12 | 2030 | Runner-up in Fenwick screening
PL-010 | Brayton Moor BESS | UK | BESS | 80 | Screening | 0.1 |  | Kwame Mensah | Grid headroom check | 2026-11-30 | 2030
PL-011 | Thy Solar Park | DK | Solar PV | 72 | Early development | 0.25 |  | Henrik Larsen | Local plan amendment | 2027-04-30 | 2029 | Municipality supportive
PL-012 | Skagen Nord Wind | DK | Onshore wind | 36 | Development | 0.45 |  | Henrik Larsen | EIA submission | 2027-02-26 | 2029 | Danish onshore tender 2026 candidate
PL-013 | Vejle Fjord Hybrid | DK | Wind + Solar | 58 | Screening | 0.1 |  | Henrik Larsen | Landowner meetings | 2026-12-11 | 2030
PL-014 | Lüneburg Heide Solar | DE | Solar PV | 92 | Development | 0.45 |  | Henrik Larsen | B-Plan decision | 2027-06-30 | 2029 | Municipal development plan in preparation
PL-015 | Uckermark Repowering | DE | Onshore wind | 54 | Acquisition | 0.5 |  | Henrik Larsen | Data room | 2026-11-20 | 2029 | Replace 18 old 1.5 MW turbines with 9 × 6 MW
PL-016 | Dithmarschen BESS | DE | BESS | 60 | Early development | 0.25 |  | Kwame Mensah | Grid request | 2026-12-15 | 2029
PL-017 | Altmark Solar | DE | Solar PV | 110 | Screening | 0.1 |  | Henrik Larsen | Site screening | 2027-01-15 | 2030
PL-018 | Halland Wind | SE | Onshore wind | 120 | Development | 0.45 |  | Henrik Larsen | Environmental permit | 2027-09-30 | 2031 | Defence radar consultation pending
PL-019 | Gotland Solar & Storage | SE | Solar + BESS | 45 | Screening | 0.1 |  | Henrik Larsen | Grid capacity check | 2027-02-26 | 2030
PL-020 | Värmland Wind | SE | Onshore wind | 150 | Early development | 0.25 |  | Henrik Larsen | Municipal veto clarification | 2027-03-31 | 2031
PL-021 | Fenwick Battery Storage | UK | BESS | 100 | Early development | 0.25 |  | Kwame Mensah | Grid offer | 2027-06-30 | 2029 | Land option signed 2026-04-30; grid application 2026-07
PL-022 | Carrick Firth Solar | UK | Solar PV | 38 | Screening | 0.1 |  | Liam McAllister | Landowner HoT | 2026-12-04 | 2029
PL-023 | Dunmore Wind | UK | Onshore wind | 72 | Development | 0.45 |  | Henrik Larsen | Planning submission | 2027-08-31 | 2031 | Peat survey completed
PL-024 | Eastholm Port BESS | UK | BESS | 40 | Screening | 0.1 |  | Kwame Mensah | Port lease discussion | 2027-01-29 | 2029 | Synergy with Green Hydrogen Pilot
PL-025 | Westerby Solar | UK | Solar PV | 60 | Early development | 0.25 |  | Liam McAllister | Scoping | 2027-02-12 | 2029
PL-026 | Mid Jutland Wind | DK | Onshore wind | 42 | Screening | 0.1 |  | Henrik Larsen | Neighbour dialogue | 2027-03-15 | 2030
PL-027 | Ostfriesland Repowering | DE | Onshore wind | 48 | Development | 0.45 |  | Henrik Larsen | BImSchG permit | 2027-05-28 | 2029
PL-028 | Kiel Bay BESS | DE | BESS | 50 | Screening | 0.1 |  | Kwame Mensah | Site screening | 2026-12-18 | 2029
PL-029 | Sörmland Solar | SE | Solar PV | 66 | Screening | 0.1 |  | Henrik Larsen | Site screening | 2027-04-16 | 2030